CALLING FOR PROPOSAL

CONSULTING SERVICES

Purchaser:			World Wide Fund for Nature – Viet Nam

(WWF-Viet Nam)

Project:			USAID Biodiversity Conservation- VFBC project

Name of Package: 	Assessment of the current scale of impacts on biodiversity of snaring and livestock grazing in Vietnam’s protected areas (SUFs and PFs)

Bid reference number:	FY25/0676 BCA

Submission Deadline: 	December 19th, 2024 17:00 (ICT)

Issued on: 05 December 2024

TABLE OF CONTENTS

Part One. Scope of Consultancy Work

Part Two. Instructions for Consultants

Chapter I. Requirements on request for proposal

Chapter II. Form

ABBREVIATIONS AND ACRONYMS

| DVTV | Dịch vụ tư vấn (Consulting service) |
| --- | --- |
| WWF | World Wide Fund for Nature (World Wide Fund for Nature) |
| HSMDX | Hồ sơ mời đề xuất (Calling for Proposal) |
| HSDX | Hồ sơ đề xuất (Proposal) |

Part I

Scope of CONSULTANCY Work

# ASSESSMENT OF THE CURRENT SCALE OF IMPACTS ON BIODIVERSITY OF SNARING AND LIVESTOCK GRAZING IN VIETNAM’S PROTECTED AREAS (SUFs and PFs)

# Background

The USAID Biodiversity Conservation Activity (the Project) is a 5-year project (2020 – 2025) that aims to maintain and increase forest quality and protect and stabilize wildlife populations in high conservation value provinces: Ha Tinh, Lam Dong, Ninh Binh, Quang Binh, Quang Nam, Quang Tri, and Thua Thien-Hue. The project targets 14 special-use forests (SUFs) and seven protection forests (PFs), linking forest management units across the landscape to maintain forest cover and connectivity of habitats vital for the protection of Vietnam’s threatened and endemic species. The project is implemented by WWF-US, in collaboration with the project partners WWF-Viet Nam, Education for Nature Vietnam (ENV), Fauna & Flora (formally Fauna and Flora International – FFI) Vietnam Programme, Re:wild, the International Union for the Conservation of Nature Vietnam (IUCN), and the Leibniz-Institute for Zoo and Wildlife (IZW).

USAID-funded Biodiversity Conservation component has four strategic approaches (SAs):

SA1: Promote Conservation-Friendly Enterprises in Forest Dependent Communities

SA2: Strengthen Management of Special-use and Protection Forests

SA3: Increase Functionality of Law Enforcement Systems for Forest and Wildlife Crimes

SA4: Minimize consumption demand through behavioral change methods

Vietnam’s protected areas face several pressures and threats, and in response the USAID BCA Project is working with government partners to address through capacity building for improved protected area management. Some challenges still require more specific attention to identify the drivers and underlying factors that are responsible for these pressures and threats to persist. In particular, it is observed that although there have been significant investments in improving law enforcement patrols that has resulted in some measurable improvements, the use of snares and traps remains a pervasive threat to wildlife populations in particular. The grazing of livestock inside in protected areas, on the other hand, and while also pervasive, has yet to be adequately addressed.

Snares endanger many species of wildlife, risking the destabilization of these ecosystems. Livestock grazing not only disrupts the natural habitats of wildlife species but also raises concerns about disease transmission between domesticated animals, wildlife, and humans. Therefore, a comprehensive assessment of snares and livestock grazing and their combined impacts on biodiversity conservation. This assessment will inform management measures and policy advocacy efforts tor minimize the impacts of snare use and cattle grazing.

# Goals and objectives

The goal of this assessment is to support the Department of Forestry (DoF), local governments, and protected area management boards (SUF and PF) in developing management responses to the negative impacts of snaring and livestock grazing on biodiversity conservation. For snaring, there is a need to identify what is already working in the law enforcement approach, and to clearly identify the gaps. For cattle grazing, there is a need to address risks associated with disease transmission between cattle and wildlife, and between wildlife and humans with cattle as vectors, as well as to find realistic solutions to ensure the livelihoods of local communities are taken into account. This goal will be achieved through the following objectives:

Assess the status of snaring and analyze the available data in Protected Areas; Assess the status of livestock grazing and analyze the available data of snares in Protected Areas.

Evaluate the adverse effects and impacts of snares and livestock grazing on biodiversity, particularly on wildlife habitats within protected areas.

Identify and recommend management solutions for regulating the use of snares and livestock grazing within and around protected areas. Assess possible risks.

# Tasks

Under the technical supervision of WWF-Viet Nam and in close coordination with protected area management boards, the consultant(s) will undertake the following tasks:

Conduct a comprehensive analysis of policies and regulations related to the use of snares, traps, and livestock grazing in and around SUFs and PFs, and develop a policy analysis report.

- The analysis will emphasize how these policies empower protected area managers and relevant government agencies to:

- Restrict, regulate, deter, or prohibit the use of snares and livestock grazing in the protected areas

- Allocate protected area budgets and secure additional funding for implementing management and mitigation measures against both snaring and grazing impacts

- Engage with local governments to establish livelihood support initiatives aimed at minimizing or ceasing livestock grazing and reducing snare usage within protected areas

- The policy analysis report will include:

- Findings and conclusions of the policy analysis, including insights into current snare regulations and enforcement gaps.

- Approaches and methodologies for conducting surveys, including coordination and facilitating agreement with collaborative management institutions, with an added focus on mapping snare hotspots.

- Criteria to select at least 5 protected areas for the field surveys, considering landscape typology, biodiversity and ecological integrity, geographical coverage, population density, poverty level, and prevalence of snare-related threats. These criteria will be jointly established with WWF.

- A detailed timeline with key milestones for both livestock and snare-related assessments.

Conduct a comprehensive assessment of the status of livestock grazing and analyze available data of snares, as well as their impacts on biodiversity, including but not limited to:

- Using official statistics and field verification, assess the presence of cattle grazing and the distribution of snares within protected areas. Evaluate the impacts of grazing and snares on the local ecology and wildlife, and analyze historical trends over the past twenty years, projecting future scenarios for the next ten years.

- Describe grazing regimes employed by local villagers and other livestock owners, while mapping and analyzing snare locations and the frequency of snare usage based on field surveys.

- Assess the current impacts of grazing and snaring activities on biodiversity, particularly on wildlife habitats, through interviews with protected area managers, communities, and field surveys. Develop scenarios to depict potential ecological impacts over the next ten years.

- Collaborate with protected area managers and multi-stakeholder management committees to identify potential mitigation and management plans. These may include:

          - Management measures feasible within current budgets to control both grazing and snaring activities

          - Collaborative management approaches with local governments, including securing access to government funding

          - Livelihood support alternatives that the Goverment can propose, in collaboration with provincial and district governments, and with multi-stakeholder management committees, to reduce cattle grazing and snare use inside protected areas

Produce a draft snaring and livestock grazing survey report and organize a technical workshop to present the findings. Workshop participants will include representatives of DoF, IUCN, BCA, NGOs, PA management boards, scientific institutions, experts, and relevant stakeholders. Revise the report based on feedback received during the workshop.

Produce the final report on the assessment of snaring and livestock grazing in protected areas and their impacts on biodiversity in Vietnam, including recommendations for effective management strategies.

# Deliverables and schedule

|  | Deliverable | Tasks included | Qty | Submission date | Form and copies |
| --- | --- | --- | --- | --- | --- |
| I | Policy analysis report | 1 | 1 | One week after signing the contract. | Electronic form in English and Vietnamese |
| II | Draft Final snaring and cattle grazing impact report | 2-3 | 1 | After finishing surveys 03 weeks |  |
| III | Final report | 4 | 1 | One week after the workshop |  |

# Period and mode of implementation

Activities are carried out in Hanoi and some project provinces.

Estimated completion time within 03 months, from January to March 2025.

# Required personnel

The task will be carried out by a team of two members:

| POSITION | RESPONSIBILITIES | ESTIMATED NUMBER OF WORKING DAYS |
| --- | --- | --- |
| Team Leader - Protected area management and conservation specialist | The specialist will lead the assessment, focusing on analyzing policy frameworks, evaluating the impacts of livestock grazing and snares on biodiversity, and developing practical management solutions. This includes liaising with local and national government stakeholders, protected area managers, and relevant NGOs. The specialist will guide the overall approach, ensuring that the assessment’s goals align with biodiversity conservation objectives. | 40 |
| GIS, data analysis expert | Support data collection, data analysis, and mapping, with a particular focus on geospatial information systems (GIS) and the analysis of data on livestock grazing and snare usage. Responsible for creating and interpreting maps, managing spatial data, and producing analysis outputs for the assessment report. | 30 |

#### Team Leader - Protected Area Management and Conservation Specialist

##### Qualification

Post graduate in conservation, forestry, biology or other related fields.

##### Professional experience

- A background in wildlife conservation, policy development, or a related field

- Demonstrated experience in developing strategies related to wildlife management, and wildlife farming

- Familiarity with the political and cultural context of Vietnam

- Should have at least 20 years of experience

Strong analytical, research, and communication skills.

Have the role of the team leader for at least one similar activities

Have at least 2 similar activities related to making risk assessment in conservation, particularly livestock grazing and snares

Proficiency in English is advantageous

Have experience in working with management board is advantageous

#### GIS and Data Analysis Expert

##### Qualification

- Bachelor’s degree (Master’s preferred) Environmental Science, Ecology, or a related field

##### General experience

- A minimum of 5 years of experience in GIS and spatial data analysis, especially in ecological or conservation contexts

- Proven experience working with geospatial data related to biodiversity, habitat mapping, or human impacts on protected areas

Specific experience

- Demonstrated ability to perform spatial analysis, including mapping of wildlife threats and habitat degradation

- Experience with mapping and analyzing patterns of human-wildlife conflict, grazing activities, or poaching within protected areas is strongly preferred

- Familiarity with relevant data sources, including remote sensing, satellite imagery, and ground-truthing methodologies

Technical Skills

- Proficiency in GIS software (e.g., ArcGIS, QGIS) and data analysis tools (e.g., R, Python)

- Skilled in data visualization and creating informative, clear, and professional-quality maps

- Familiarity with remote sensing data and spatial modeling techniques is advantageous

Additional Skills

Strong analytical and problem-solving abilities, with a keen eye for detail

Excellent communication skills for report writing and presentation of GIS findings

Proficiency in English is advantageous, as is experience working with Vietnamese governmental and conservation bodies

# Special requirement

Reports and documents used for the workshop must comply with regulations on using logos and report templates of USAID and WWF-Vietnam.

The report must clearly state the project name: "Biodiversity Conservation Component, Sustainable Forest Management and Biodiversity Conservation Project (VFBC), funded by the United States Agency for International Development (USAID). Sponsored, WWF coordinates with the Ministry of Agriculture and Rural Development to implement.

Part 2

INSTRUCTIONS TO CONSULTANTS

Chapter I – CALLING FOR PROPOSAL

Section 1. Content of Calling for Proposal

1. Purchaser: World Wide Fund for Nature – Viet Nam (WWF-Viet Nam) would like to request for an proposal from eligible consulting groups (hereinafter called Consultants) who are interested in submitting the proposal for “ASSESSMENT OF THE CURRENT SCALE OF IMPACTS ON BIODIVERSITY OF SNARING AND LIVESTOCK GRAZING IN VIETNAM’S PROTECTED AREAS (SUFs and PFs)”

2. The contents, Scope of works, deliverables, and specific requirements on implementation timeline, experience, and qualifications of consultants are presented in Part One – Scope of Work.

Section 2. Language

The proposal, as well as all documents exchanged between the purchaser and the consultant relating to the request for proposal, will be written in Vietnamese or English.

Section 3. Proposal contents and timeline

The proposal prepared by the consultant must include the following contents:

            - Letter of Interest using Form-1;

            - Agreement to establish a consulting group using Form-2;

            - A curriculum vitae stating relevant experiences and qualifications of each consultant with the signature of the consultant (use the own form of consultant or Form-5);

            - In case the consultant has performed similar bidding packages performed by the team or by members of the consulting team, the consultant can list them on Form-3. Consultants who do not carry out similar bidding packages can skip;

            - Confirming participants in the bidding package using Form-4;

            - Technical and Financial proposal using Form-6

Proposal dealine submission: 90 days since bid submission deadline date.

Section 4. Details of submission:

Please send the electronic proposal to WWF-Viet Nam’s designated mailbox at lien.caoquynh@wwf.org.vn; duc.dominh@wwf.org.vn; and hung.phamquoc@wwf.org.vn Your e-mail must have the subject heading as: “HSDX-[Consultant’s name]- FY25/0676 BCA “Assessment of the current scale of impacts on biodiversity of snaring and livestock grazing in Vietnam’s protected areas (SUFs and PFs)”.

The maximum size per email that WWF-Viet Nam can receive is 25MB.

Section 5. Deadline for submission

1. Consultants can send their proposal via email to WWF-Vietnam's address, but must ensure that the purchaser receives the proposal on or before 17:00, December 19th , 2024 (Hanoi time – ICT).

2. The purchaser may extend the submission deadline in case the number of proposals needs to be increased or when the purchaser considers it essential to amend the proposal.

3. When extending the submission deadline, the purchaser will notify the Consultants in written form that have submitted their proposals, and at the same time publicly post the notice of extension of the submission deadline. Consultants who have submitted proposals can receive them back to amend and supplement their proposals. In case the Consultant does not receive back the submitted proposal and does not send back the amended and supplemented proposal before the extension time, the purchaser will preserve such proposals and consider it as the official and valid proposal of the Consultant and will conduct a review of the following submissions according to the newly extended deadline.

Section 6. Late submission

Proposals sent to the purchaser after the deadline for submission will not be opened and returned to the Consultant in their original state. Any documents sent by the Consultant after the deadline for submission of documents to amend and supplement the submitted Proposal are invalid, except for the documents sent by the Consultant to clarify the Proposal at the request of the purchaser for clarifying or supporting documents to demonstrate the Consultant's eligibility, competency, and experience.

In case after the deadline for submission of the proposal, the purchaser discovers that the Proposal lacks documents proving its eligibility, capacity, and experience, the Consultant is allowed to send documents to the purchaser within a period of time to clarify their eligibility, capacity, and experience. The purchaser is responsible for receiving the clarification documents of the Consultant for consideration and assessment; additional documents, clarifications on eligibility, qualifications, and experience are considered part of the application. The purchaser will notify the Consultant of receipt of additional clarifications from the Consultant.

Section 7.  Conditions for the evaluation

Consultants will be considered and selected for evaluation when fully meet the following conditions:

1. Proposals with sufficient information as required in Section 3;

2. Having the Proposal that meets the requirements stated in the Scope of Service for consulting services and the requirements of this Proposal.

Section 8. Result announcement and evaluation

Selection will be made through domestic competitive bidding procedures as outlined in this Call for Proposals and is open to all qualified consultants as defined in the Standard Terms. USAID M6 standard - Procurement Policy for Non-US Entities. Geocode 937 applies to USAID Biodiversity Conservation projects. For more detailed information about Geocode 937, please refer to:

ADS Chapter 310: Source and Nationality Requirements for Procurement of Commodities and Services Financed by USAID | U.S. Agency for International Development

Shortlisted candidates will be invited for interviews if necessary and evaluated against the above criteria of competence, experience and technical and financial proposal.

Chapter 2 - FORM

The consultants prepare required forms as follows:

| No | Content | Forms |
| --- | --- | --- |
| 1 | Letter of Interest | Form- 1 |
| 2 | Agreement to establish a consulting group | Form- 2 |
| 3 | Consultant's Experience and Competencies | Form- 3 |
| 4 | Statement of availability | Form- 4 |
| 5 | Professional resume | Form- 5 |
| 6 | Technical and Financial proposals | Form- 6 |

Form- 1 – Letter of Interest

__________, date ___ month ___ year ___

To: The World Wild Fund for Nature-Representative Office in Viet Nam

Having carefully examined the Calling for Proposal dated [insert date] for the assignment [insert number and name of the package], we, consultant group with ….(name of team leader) as a team leader, expression of interest to participate in this package. We are hereby submitting our Technical and financial proposal for conducting this assignment.

We have read carefully the requirement in the scope of work.

This Proposal document will be valid for 90 days from the date of submission deadline. If we are being selected to implement this assignment, we commit to meet in requirement of timeline, deliverable, we will participate in bidding package ____ [insert name of consulting package].

We commit that the information declared in this document is accurate and truthful.

We commit that we are not on the list of entities that are not allowed to participate in the bidding according to USAID regulations

We hereby declare that all the information and statements made in this Proposal are true and accept that any misinterpretation contained in it may lead to our disqualification.

We agree that WWF-Vietnam reserves the right to refuse any application of interest that does not meet the requirements outlined in the request for expression of interest. In the circumstances specified in its procurement policy, WWF-Vietnam may cancel the entire EOI process for the implementation of the tender package and proceed with the request for EOI again.

Representative of the consulting group or all members

[Signature and full name]

# Form- 2 - Agreement to establish a group of consultants

__________, date ___ month ___ year ___

Tender Ref: ________ [insert name of the package]

Project: ____________ [insert name of the project]

- According to the request for proposals the bidding package ______ [insert name of the package] dated ____ month ____ year __ [Date stated in the request for proposals];

We include:

Name of consulting group members ____ [insert name of each member]

Address: ____________________________________________________________________

Cel: _________________________________________________________________

E-mail: ____________________________________________________________________

The parties (referred to as members) agree to sign an agreement to establish a consulting group with the following contents:

Article 1. General principles

1. The members voluntarily form a consulting group to participate in the selection of requests for proposals in the bidding package ___ [insert name of the bidding package].

2. The members agree that the name of the consulting group for all transactions related to the bidding package is: Consulting group [insert name of team leader].

3. The members commit that no party can voluntarily participate independently or cooperate in any way with another party to participate in this bidding package.

Article 2. Assignment of responsibilities

The members agree to take joint responsibility and separate responsibility for the implementation of the ____ insert name of the bidding package] as follows:

1. The leading member of the Consultant Group (team leader)

The members agree to authorize ____ [insert name of one member] as the leading member of the Consultant Group, representing the Consultant Group in the following tasks:

[- Sign letter of interest;

- Sign documents for the transaction with the purchaser during the selection process, including the written request for clarification of the request for proposals and the written explanation and clarification of the request for proposals (if any).(3)

2. Expected responsibilities of each member of the Consulting Group to implement the bidding package:

The participating parties are expected to assign responsibilities of each member as follows: ___ [Insert expected main job content of each member, including the leading member].

Article 3. Effect of the agreement

The Agreement takes effect from the date of signing and terminates in the following cases:

1. The consulting group may not be selected to implement the above-mentioned bidding package;

2. Cancellation of selection for bidding packages according to notices of the purchaser.

The agreement to establish the consulting group is made in ______ copies, each party keeps ______ copies with equal legal validity.

Representative of the consulting group or all members

[Signature and full name]

Form- 3 – CONSULTANT’S EXPERIENCE

Please list similar work packages done, if any, if not, skip this table

Similar service packages are carried out by the Consulting Group, or by members of the Consulting Group. (Each job/contract is presented in a separate table)

| Name of project |  |
| --- | --- |
| Location |  |
| Purchaser |  |
| Bidding package name |  |
| Contract prices |  |
| Name of participating constultant group members: |  |
| Role to participate in the bid (consulting group, independent consultant, member of a consulting organization) |  |
| Contract performance time (insert according to the time specified in the contract; specify from date.... to date...) |  |
| Summary of specific tasks performed by the consultant under the contract |  |

The consultant encloses copies of the Contracts listed above.

Representative of the Consulting Group

[Signature and full name]

Form- 4 - STATEMENT OF AVAILABILITY

I (We), the undersigned …………………………………………………………………………….

State that the proposed named expert(s) listed below is/are available to carry out the services relating to the Request for Proposal dated [insert date] mentioned above as from ………………, for the period initially envisaged in the proposal submitted.

| No | Expert’s Name | Title/Position | Duration |
| --- | --- | --- | --- |
| 1 |  |  |  |
| 2 |  |  |  |
| 3 |  |  |  |
| … |  |  |  |

I (We) understand that failure to make the named expert(s) listed above available for the performance of the services may lead to the cancellation of the Contract if the justification provided for the personnel change is not accepted by WWF Viet Nam in advance

Signature and stamp:

Name on behalf of the Consultant:

Title:

Date: _________________________________

Form- 5 - CURRICULUM VITAE (VC) FOR PROPOSED KEY CONSULTANTS

Use an existing resume or use the attached template. This should includes resumes of both consultants

Proposed Position (only one candidate shall be nominated for each position):

Name of Consultant (Insert full name):

Date of Birth: 	 Citizenship:

Education (Indicate college/university and other specialized education of expert, giving names of institutions, degrees obtained, and dates of obtainment):

Membership in Professional Associations:

Working experience:

| Duration | Name of organization | Position |
| --- | --- | --- |
| From month…date…to month…date… | … | …. |

Expected tasks assigned in the bidding package:

| Details of expected tasks assigned in the bidding package: | [Nêu kinh nghiệm thực hiện những công việc, nhiệm vụ liên quan trước đây để chứng minh khả năng thực hiện công việc, nhiệm vụ được phân công] [Indicate previous experience in performing related tasks to prove your ability to perform assigned tasks] |
| --- | --- |
| [Indicate the tasks that experts are assigned to perform] |  |
| ... |  |

Năng lực: [Mô tả chi tiết kinh nghiệm và các khóa đào tạo đã tham dự đáp ứng phạm vi công tác được phân công. Trong phần mô tả kinh nghiệm cần nêu rõ nhiệm vụ được phân công cụ thể trong từng dự án và tên/địa chỉ của chủ đầu tư/bên mời thầu.]

Competency: [Describe in detail the experience and training courses attended to meet the assigned scope of work. In the description of experience, it is necessary to clearly state the specific tasks assigned to each project and the name/address of the investor/procuring]

Qualification (Indicate significant training since degrees)

Languages (For each language indicate proficiency: good, fair, or poor in speaking, reading, and writing):

Contact information: [Specify name, phone number, email of the person to be contacted for information verification]

I hereby certify that the above information is true, if wrong, I will take responsibility before the law.

______, date, month,  year _____

[Signature and full name]

Note:

- Each individual consultant on the list mentioned in Form-4 must declare this Form.

- Upon request, the Consultant will send copies of the contract to the soliciting party; Photocopy of diploma, professional practice certificate.

Form- 6-

TECHNICAL AND FINANCIAL PROPOSALS

CONSULTING SERVICES

Purchaser			World Wide Fund for Nature – Viet Nam

(WWF-Viet Nam)

Project:			USAID Biodiversity Conservation - VFBC project

Name of Package:

Bid reference number:

Consultant’s information:

I. Understand the ToR and objective of the activity

II. Main task and activities

III. Technical approach and methodology

| Task | Methodology |
| --- | --- |

IV. Work plan

The consultant can use the schedule of time according to the form below:

| No. | Tasks/Activities | Consultant’s name | Tentative timeline | Man-day | Location | Travel day |
| --- | --- | --- | --- | --- | --- | --- |
| I | Task 1 |  |  |  |  |  |
| 1 | … |  | … |  |  |  |
| 2 | … |  | … |  |  |  |
| … | … |  | … |  |  |  |
| II | Task 2 |  |  |  |  |  |
| 1 | … |  | … |  |  |  |
| 2 | … |  | … |  |  |  |
| III | Task 3 |  |  |  |  |  |
| 1 | … |  |  |  |  |  |
| 2 | … |  |  |  |  |  |
| … | … |  |  |  |  |  |
|  | Total |  |  |  |  |  |

IV. Deliverable and timeline

| No. | Task | Deliverable | Timeline |
| --- | --- | --- | --- |
| 1 | Task 1 |  | ….days after signing the contract |
| 2 | Task 2 |  | ….days after signing the contract |
| 3 | Task … |  | ….days after signing the contract |

VI. Financial proposal

Note: Travel and accommodation expenses should be proposed following the technical proposal. It will be calculated following WWF’s regulations. Please kindly take the cost norm of WWF on the last page for reference when preparing the financial proposal. The WWF’s cost norm will be the ceiling rate that can be acceptable. The financial proposal will be evaluated based on the best price offer which includes all related costs to conduct this assignment as broken down in the below tables. Please kindly share the calculation on an Excel file for our reference and finance check.

      - Table 1: COST CALCULATION FOR PACKAGE

| 1. Consultancy fee (including applicable taxes) | Unit | Q’ty | Unit price | Total |
| --- | --- | --- | --- | --- |
| 1.1 | Day |  |  |  |
| 1.2 | Day |  |  |  |
| Sub-Total |  |  |  |  |
| 2. Allowance & Accommodation (including applicable taxes) |  |  |  |  |
| 2.1 |  | ... |  |  |
| 2.2 |  | ... |  |  |
| … |  |  |  |  |
| Sub-Total |  |  |  |  |
| 3. Travel & Transport Cost (including applicable taxes) |  |  |  |  |
| 3.1 Vehicle lease/rent |  | ... |  |  |
| 3.2 Air-tickets |  | ... |  |  |
| Sub-Total |  |  |  |  |
| 4. Other costs (including applicable taxes) |  |  |  |  |
| 4.1 |  | ... |  |  |
| 4.2 ... |  | ... |  |  |
| Sub-Total |  |  |  |  |
| … |  |  |  |  |
| Grand total |  |  |  |  |

#### Table 2: DETAILED COST BREAKDOWN PER TASK

Task/Deliverable 1:

| 1. Consultancy fee (including applicable taxes) | Unit | Q’ty |  | Unit price | Total |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Day |  |  |  |  |
| 1.2 | Day |  |  |  |  |
| Total |  |  |  |  |  |
| 2. Allowance & Accommodation (including applicable taxes) |  |  |  |  |  |
| 2.1 |  | ... |  |  |  |
| 2.2 |  | ... |  |  |  |
| … |  |  |  |  |  |
| Total |  |  |  |  |  |
| 3. Travel & Transport Cost (including applicable taxes) |  |  |  |  |  |
| 3.1 Vehicle lease/rent |  | ... |  |  |  |
| 3.2 Air-tickets |  | … |  |  |  |
| …. |  | ... |  |  |  |
| … |  |  |  |  |  |
| Total |  |  |  |  |  |
| 4. Other cost (including applicable taxes) |  |  |  |  |  |
| 4.1 |  | ... |  |  |  |
| 4.2 ... |  | ... |  |  |  |
| Total |  |  |  |  |  |
| … |  |  |  |  |  |
| Grand total |  |  |  |  |  |

Task/Deliverable 2:

| 1. Consultancy fee (including applicable taxes) | Unit | Q’ty |  | Unit price | Total |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Day |  |  |  |  |
| 1.2 |  |  |  |  |  |
| Total |  |  |  |  |  |
| 2. Allowance & Accommodation (including applicable taxes) |  |  |  |  |  |
| 2.1 |  | ... |  |  |  |
| 2.2 |  | ... |  |  |  |
| … |  |  |  |  |  |
| Total |  |  |  |  |  |
| 3. Travel & Transport Cost (including applicable taxes) |  |  |  |  |  |
| 3.1 Vehicle lease/rent |  | ... |  |  |  |
| 3.2 Air-tickets |  | … |  |  |  |
| …. |  | ... |  |  |  |
| … |  |  |  |  |  |
| Total |  |  |  |  |  |
| 4. Other cost (including applicable taxes) |  |  |  |  |  |
| 4.1 |  | ... |  |  |  |
| 4.2 ... |  | ... |  |  |  |
| Total |  |  |  |  |  |
| … |  |  |  |  |  |
| Grand total |  |  |  |  |  |

Task/Deliverable 3:

……

I understand that WWF-Vietnam is not bound to accept any Proposal received.

Consultant

Sign and full name

WWF’s cost norm for reference:

Daily allowance:

Daily allowance 1 day = 02 lunches and dinners. If any meal was provided, it will be deducted from the daily allowance at the rate of 50% for 1 meal. Location; Daily allowance (VND). Cities and province, Tourist site; 600,000. District, commune; 450,000.

Airport transfer fee:

Actual payment or following the norm below:

| No. | Airport | Location | Cost norm for one way (from or to airport) |
| --- | --- | --- | --- |
| 1 | Noi Bai | Ha Noi | 350,000 |
| 2 | Vinh | Vinh City | 125,000 |
| 3 | Dong Hoi | Dong Hoi city, Quang Binh province | 170,000 |
| 4 | Phú Bài | Hue City, Thua Thien Hue province | 260,000 |
| 5 | Da Nang | Da Nang city | 100,000 |
| 6 | Chu Lai | Tam Ky, Quang Nam | 460,000 |
| 7 | Lien Khuong | Da Lat city | 260,000 |
| 8 | Tan Son Nhat | Ho Chi Minh city | 180,000 |

Accommodation:

| Location | Maximum rate/pax/night |
| --- | --- |
| Centrally run cities, Hue City, Da Nang City | 1,800,000 |
| Cities and province, tourist site | 1,500,000 |
| District, commune | 800,000 |
| Support if staying at or relative’s house friends’shouse | 200,000 |

Even though Protection Forests (PF) do not have a formal biodiversity conservation function, many have high biodiversity values and should be assessed to the same extent as Special Use Forests (SUF) to inform management.