TERMS OF REFERENCE

Consultancy on delivering Communication materials and products for WWF-Viet Nam’s Forest Practice

Time: Feb – June 2022

Location: Ha Noi or Hue

Reporting to: Media & Biodiversity Conservation Communications Manager

I. Background

WWF is one of the world’s largest and most experienced independent conservation organizations, with almost five million supporters and an active global network across more than 100 countries. WWF’s mission is to stop the degradation of the planet’s natural environment and to build a future in which humans live in harmony with nature.

WWF was one of the first international non-governmental organizations to work in Vietnam. In 1985, WWF began working on a national conservation strategy, and since then has worked closely with the Vietnamese Government on a diverse range of environmental issues and implemented field activities across the country.

WWF has worked, for decades in Viet Nam, to protect the pristine forests that are rich in biodiversity and important carbon sinks. Our works and approaches are diverse from forest enrichment to reforestation; from promoting community forest management to forest sustainable plantation; improving forest governance at local and national levels; establishing sustainable market links.

Our forest program in Viet Nam is beginning to implement the next 5 year strategy(*) that focusing on:

- Mitigating the footprint of the Vietnamese forest sector domestically and globally;

- Ensuring forests in Protected Areas in the Central Annamites Landscape are under sufficient protection or improved management;

- Expanding the forest area under formal protection and ensuring effective conservation;

- Conserving watershed protection forests using sustainable forest management plans;

- Increasing the number of well-managed forests under credible certification with improving forest quality;

- Engaging more communities in sustainable forest management and protection to improve local livelihoods through sustainable financing mechanisms;

- Restoring important forest corridors and fragmented areas;

- Maintaining a rate of natural forest cover loss below 0.3%;

- Continuing to explore innovative intervention strategies to enhance forest protection and biodiversity conservation.

Communications play an important role in leveraging our forest works to our target audience (TA) who are the local communities, government and business partners, donors and the public. WWF-Viet Nam is looking for an individual consultant who will support to implement a number of communication activities to deliver our messages to the target audience.

II. Scope of Work

The consultant is expected to:

- Study the communication guidelines of WWF;

- Study the works of WWF-Viet Nam’s forest programme to have an overview of the programme;

- Working with Forest Practice Lead, project managers and Core communication team of WWF-Viet Nam to consult/ design/edit numerous of comm products (details in Annex A);

- Making distribution plan for the products and implement it;

- Consultant /agency also expected to deliver unplanned / ad-hoc tasks when needed.

III. Qualifications

The consultant is required to have:

- Obtained a Bachelor’s degree in Marketing, Communications or related field or 5 years of experience in communications work;

- Excellent communication skills in both written and spoken English and Vietnamese;

- Good understanding and background on conservation issues;

- Passionate about communications and conservation;

- Has been worked with WWF is a plus;

- Demonstrated ability to adhere to strict confidentiality;

- Can Do attitude;

- Experience in designing and / or photography will be an advantage;

- Adheres to WWF’s values, which are: Courage, Respect, Integrity and Collaboration;

IV. How to submit your proposal

Interested consultants are kindly requested to send technical and financial proposals in English:

Via email: ngan.nguyenphuong@wwf.org.vn with subject: [ Forest Comm consultancy]

Deadline for submission is 4 PM Feb 14th 2022, Ha Noi time.

Only short-listed consultants will be contacted.

Annex A

Communications Output for Forest Programme

| No | Project | Requirement | Timeline |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Dec | Jan | Feb | Mar | Apr | May | Jun |
|  | IKEA |  |  |  |  |  |  |  |  |
| 1 | FSC Practical Guidebook (50 pages) | - Language editing - Facilitate the designing (propose designer for WWF to choose; working with the designer to make a digital version; make sure the design is in line with WWF's style and brand guideline) |  |  |  |  |  |  |  |
|  | Leading to Change |  |  |  |  |  |  |  |  |
| 2 | Documentary CFM models | - Write up 5 documents (2-4 pages each) based on technical content from project - Facilitate designing for these 5 documents |  |  |  |  |  |  |  |
| 3 | A film on Tam My Tay model | - Propose film consultant for WWF to choose (including writing TOR) - Working with film consultant and WWF team to produce the film - Working with WWF Comm and staff to distribute the film |  |  |  |  |  |  |  |
|  | Landscape Resilience Fund |  |  |  |  |  |  |  |  |
| 4 | Project brochure | - Develop content in both English and Vietnamese - Facilitate the designing and printing |  |  |  |  |  |  |  |
| 5 | Sub webpage | - Developing content; made both in English and Vietnamese version) |  |  |  |  |  |  |  |
|  | DCFD - CAL |  |  |  |  |  |  |  |  |
| 6 | Case studies | - Write up a successful case study |  |  |  |  |  |  |  |
| 7 | Film | - Propose film consultant for WWF to choose (including writing TOR) - Working with film consultant and WWF team to produce the film - Working with WWF Comm and staff to distribute the film |  |  |  |  |  |  |  |
|  | CARBI II |  |  |  |  |  |  |  |  |
| 8 | Producing leaflets for GRM for CarBi 2 | - Develop messages & contents for the products - Facilitating the designing & printing process |  |  |  |  |  |  |  |
|  | GENERAL |  |  |  |  |  |  |  |  |
| 9 | Forest leaflet / brochure | - From existing materials, write up brochure in English and Vietnamese - Design and and request to print (if budget available) |  |  |  |  |  |  |  |